## DAY 1
DAILY EFFORT TRACKER
PLANNED ACTIVITIES | TRAINEE 1 ACTIVITIES(MODULE1) | TRAINEE 2 ACTIVITIES(MODULE 2) | TRAINEE 3 ACTIVITIES(MODULE3) | TRAINEE 4 ACTIVITIES(MODULE4) | ACTIVITY TIME | EMP_ID | TRAINEES | NAME
[6 empty] | 1039767 | TARINEE 1 | Vijay Pal
IDENTIFICATION OF DATA IN CSV | SUPPLIER_LEGACY | REQUISITION_LEGACY | PO_LEGACY | INVOICE_LEGACY_FEB19_04 | 9:30 A.M - 10:30 A.M | 1039770 | TRAINEE 2 | Aakash Shah
CREATING CTL FILE FOR SQL LOADER | XX_SUPPLIER_TEMP_04_CTL | REQUISITION_04_CTL | XX_PO_TEMP_04_CTL | XX_INVOICE_TEMP_04_CTL | 11:00 A.M - 12:30 P.M | 1039773 | TRAINEE 3 | Tannu Singh
CREATING EXECUTABLE | XX_SUPPLIER_TEMP_04_CTL_EXE | REQUISITION_STG_GRP_04 | XX_PURCHASE_ORD_04_EXE | INVOICE_MIGRATION_04_EXE | 14:15 P.M - 14:45 P.M | 1039774 | TRAINEE 4 | Gowri Shanker
CREATING CONCURRENT PROGRAM | XX_SUPPLIER_TEMP_04_CTL_PRG | REQUISITON_STG_GRP_04_PRG | XX_PURCHASE_ORD_04_PRG | INVOICE_MIGRATION_04_PRG | 14:45 P.M - 15:15 P.M
ERRORS RECTIFICATION | SQL*Loader-350: Syntax error Rectification | SQL*Loader-350: Syntax error, SQL*Loader-500: Unable to open file | Syntax error at line 39.Expecting "," or ")",found "VERIFY_FLAG". | SQL*Loader-350: Syntax error Expecting "," or ")", found "to_date" INVOICE_DATE to_date('Mm/dd/yyyy') | 15:15 P.M - 16:00 P.M
WARNINGS RECTIFICATION | ORA-01722: invalid number Rectification | ORA-01722: invalid number Rectification | ORA-01722: invalid number | ORA-01858: a non-numeric character was found where a numeric was expected | 16:30 P.M - 17:00 P.M
LOADING DATA INTO STAGING TABLE | XX_SUPPLIER_TEMP_04 | XX_PO_REQ_TEMP_04 | XX_PO_TEMP_04 | xx_ap_invoices_FEB19_temp_04 | 17:00 P.M - 17:30 P.M

## DAY 2
PLANNED ACTIVITIES | TRAINEE 1 ACTIVITIES(MODULE1) | TRAINEE 2 ACTIVITIES(MODULE 2) | TRAINEE 3 ACTIVITIES(MODULE3) | TRAINEE 4 ACTIVITIES(MODULE4) | ACTIVITY TIME
VALIDATIONS FOR THE DATA IN STAGING TABLE | DUMMY INTERFACE TABLE : AP_SUPPLIERS_INT_DUMMY_G04, INT EXE NAME: SP SUPPLIERS DUMMY INT 04 EXE, INT EXE SHORT NAME : SP_SUPPLIERS_DUMMY_INT_04_EXE, INT PRG NAME : SP SUPPLIERS DUMMY INT 04 PRG, INT PRG SHORT NAME: SP_SUPPLIERS_DUMMY_INT_04_PRG SEQUENCES VENDOR_INTERFACE_ID: SEQ_VENDOR_INT_ID_G04 VENDOR_SITE_INTERFACE_ID: SEQ_VENDOR_SITE_INT_ID_G04 |  | DUMMY INTERFACE TABLE: PO_HEADERS_INTERFACE_DUMMY_04 DUMMY INTERFACE TABLE:PO_LINES_INTERFACE_DUMMY_04 DUMMY INTERFACE TABLE:PO_DIST_INTERFACE_D_04 SEQUENCES IHEADER_ID:SEQ_PO_HEADER_ID_04 LINE_ID:SEQ_PO_LINE_ID_04 DISTRIBUTION_ID:SEQ_PO_DISTRIBUTION_ID_04 |  | 9:30 A.M - 11:30 A.M
ERROR RECTIFICATION | NO ERRORS |  | 1:ORA-01722: invalid number ORA-06512: at "APPS.SP_PO_INTERFACE_DUMMY_04", line 23 ORA-06512: at line 1 |  | 11:30 A.M - 12:00 P.M
WARNING RECTIFICATION | NO WARNINGS |  | NO WARNINGS |  | 12:00 P.M - 12:30 P.M
MOVING DATA TO THE TEMPORARY INTERFACE TABLE AND CHECKING THE VALIDATIONS | MAIN INT TABLE :SP_SUPPLIERS_INT EXE SHORT NAME :SP_SUPPLIERS_INT_04_EXE EXE NAME:SP SUPPLIERS INT 04 PRG NAME:SP SUPPLIERS INT 04 PRG PRG SHORT NAME:SP_SUPPLIERS_INT_04_PRG |  | INTERFACE TABLES : Po_lines_interface, Po_headers_interface, Po_distributions_interface INTERFACE EXE NAME: XX_PO_INTERFACE_04_EXE INTERFACE PRG NAME : XX_PO_INTERFACE_04_PRG |  | 14:30 P.M - 15:30 P.M
CHECKING IMPORT PROGRAM | SUPPLIER OPEN INTERFACE IMPORT |  | PO OPEN INTERFACE IMPORT |  | 15:30 P.M - 16:00 P.M
MOVING DATA FROM INTERFACE TABLE TO BASE TABLE | PO_VENDORS UPDATED WITH FEB19_LC1_04 DATA |  | BASE TABLES : PO_HEADERS_ALL,PO_LINES_ALL, PO_DISTRIBUTIONS_ALL UPDATED BY FEB19_LC1_04 DATA |  | 16:30 P.M - 17:00 P.M
PROJECT 2 IDEA DISCUSSION | PROJECT 2 SILICON SUPPLIER PART DISCUSSION | PROJECT 2 SILICON REQUISITION PART DISCUSSION | PROJECT 2 SILICON PRODUCT PURCHASE ORDER PART DISCUSSION | PROJECT 2 SILICON PRODUCT INVOICES PART DISCUSSION | 17:00 P.M - 17:30 P.M