## PURCHASE ORDER
EMPLOYEE NAME : TANNU SINGH EMPLOYEE_ID:1039773 GROUP NO:04 |  | DAILY EFFORT TRACKER
DAY 1
S.NO | DATE | ACIVITY | TIME | DESCRIPTION | STARTING DATE | COMPLETION DATE | STATUS | ERRORS AND WARNINGS
1 | 2019-05-31 | IDENTIFICATION OF DATA IN CSV | 9:30 A.M TO 10:30 A.M | LEGACY FILE:= PO_LEGACY
2 |  | CREATING CTL FILE FOR SQL LOADER | 11:00 A.M TO 12:30 P.M | CTL FILE TO LOAD DATA TO STAGING TABLE:= XX_PO_TEMP_04_CTL | 2019-05-31 | 2019-05-31 | COMPLETED | Syntax error at line 39.Expecting "," or ")",found "VERIFY_FLAG".
3 |  | CREATING CONCURRENT EXECUTABLE AND PROGRAM | 2:00 P.M TO 3:30 P.M | EXCECUTABLE TO RUN THE CTL FILE:= XX_PURCHASE_ORD_04_EXE PROGRAM TO RUN THE CTL FILE:= XX_PURCHASE_ORD_04_PRG | 2019-05-31 | 2019-05-31 | COMPLETED
4 |  | LOADING DATA INTO STAGING TABLE | 3:30 P.M TO 5:30 P.M | XX_PO_TEMP_04 | 2019-05-31 | 2019-05-31 | COMPLETED | ORA-01722: invalid number
DAY 2
S.NO | DATE | ACTIVITY | TIME | DESCRIPTION | STARTING DATE | COMPLETION DATE | STATUS | ERRORS AND WARNINGS
1 | 2019-06-02 | CREATION OF DUMMY INTERFACE TABLES | 9:30 A.M TO 10:00 A.M | DUMMY INTERFACE TABLES:= PO_HEADERS_INTERFACE_DUMMY_04 PO_LINES_INTERFACE_DUMMY_04 PO_DIST_INTERFACE_D_04 | 2019-06-02 | 2019-06-02 | COMPLETED
2 |  | VALIDATIONS FOR THE DATA IN STAGING TABLE | 10:00 A.M TO 12:00 P.M | PROCEDURE FOR VALIDATING DATA AND INSERTING IT INTO INTERFACE TABLES:= SP_PO_INTERFACE_DUMMY_04 SEQUENCES:= IHEADER_ID:SEQ_PO_HEADER_ID_04 LINE_ID:SEQ_PO_LINE_ID_04 DISTRIBUTION_ID:SEQ_PO_DISTRIBUTION_ID_04 | 2019-06-02 | 2019-06-02 | COMPLETED | 1:ORA-01722: invalid number ORA-06512: at "APPS.SP_PO_INTERFACE_DUMMY_04", line 23 ORA-06512: at line 1
3 |  | MOVING DATA TO THE TEMPORARY INTERFACE TABLE AND CHECKING THE VALIDATIONS | 12:30 P.M T0 2:00 P.M | EXECUTABLE NAME:= XX_PO_INTERFACE_04_EXE PROGRAM NAME:= XX_PO_INTERFACE_04_PRG | 2019-06-02 | 2019-06-02 | COMPLETED | NO ERROR
4 |  | CHECKING IMPORT PROGRAM | 2:00 P.M TO 2:30 P.M | PO OPEN INTERFACE IMPORT | 2019-06-02 | 2019-06-02 | COMPLETED
5 |  | MOVING DATA TO ACTUAL INTERFACE TABLES | 2:30 P.M TO 3:00 P.M | ACTUAL INTERFACE TABLES ARE:= PO_HEADERS_INTERFACE PO_LINES_INTERFACE PO_DISTRIBUTIONS_INTERFACE | 2019-06-02 | 2019-06-02 | COMPLETED | NO ERROR
6 |  | MOVING DATA FROM INTERFACE TABLE TO BASE TABLE | 3:30 P.M TO 4:30 P.M | BASE TABLES : PO_HEADERS_ALL,PO_LINES_ALL, PO_DISTRIBUTIONS_ALL UPDATED BY FEB19_LC1_04 DATA | 2019-06-02 | 2019-06-02 | COMPLETED
7 |  | PROJECT 2 SILICON PRODUCT PURCHASE ORDER PART DISCUSSION | 4:30 P.M TO 5:30 P.M |  | 2019-06-02 | 2019-06-02
DAY 3
S.NO | DATE | ACTIVITY | TIME | DESCRIPTION | STARTING DATE | COMPLETION DATE | STATUS | ERROR AND WARNINGS
1 | 2019-06-03 | CREATING REPORT | 9:30 A.M TO 11:00 A.M | REPORT NAME:= ITEM_WISE_PO_DETAILS_04 | 2019-06-03 | 2019-06-03 | COMPLETED | 1:ERRORS:=Routine FDPREP cannot read the file /ETAVIS/ETAVIS/fs1/EBSapps/appl/gl/12.0.0/reports/US/ITEM_WISE_PO_DETAILS_04.rep. RECTIFIED
2 |  | CREATING REPORT EXECUTABLE AND REPORT PROGRAM | 11:00 A.M TO 12:00P.M | EXECUTABLE TO RUN REPORT:= XX_PO_REP_04_EXE PROGRAM TO RUN REPORTNAME:= XX_PO_REP_04_PRG VALUESET:=VS_CURRENCY_CODE_04 | 2019-06-03 | 2019-06-03 | COMPLETED
3 |  | CREATING REPORT FEATURES IN XML PUBLISHER | 12:00P.M TO 12:30 P.M | XX_PO_REP_04_PRG_040619 | 2019-06-03 | 2019-06-03 | COMPLETED
4 |  | CREATING DATA DEFINATION CODE AND DATA TEMPLATE | 2:00 P.M TO 2:30 P.M | DATA DEFINITION:= XX_PO_REP_04_PRG_DD DATA TEMPLATE:= XX_PO_REP_04_PRG_DT | 2019-06-03 | 2019-06-03 | COMPLETED
5 |  | CHECKING REPORT PROGRAM WITH DATA TEMPLATE | 2:30 P.M TO 3:30 P.M | DT CODE:=XX_PO_REP_04_PRG_DTC | 2019-06-03 | 2019-06-03 | COMPLETED
6 |  | WORKFLOW | 3:30 P.M TO 4:00 P.M | ITEM TYPE:PO049773 PROCEDURE:=SP_WORKFLOW_PO049773 SEQUENCE FOR ITEMKEY:=SEQ_ITEMKEY_773 | 2019-06-03 | 2019-06-03 | COMPLETED
7 |  | DOCUMNETATION | 4:00 P.M TO 5:30 P.M |  | 2019-06-03 | 2019-06-03 | IN PROCESS

## REQUESTIONS
EMPLOYEE NAME : AKASH SAH EMPLOYEE_ID:1039770 GROUP NO:04 |  | DAILY EFFORT TRACKER
DAY 1
S.NO | DATE | ACIVITY | TIME | DESCRIPTION | STARTING DATE | COMPLETION DATE | STATUS | ERRORS AND WARNINGS
1 | 2019-05-31 | IDENTIFICATION OF DATA IN CSV | 9:30 A.M TO 10:30 A.M | LEGACY FILE:= REQUISITION_LEGACY
2 |  | CREATING CTL FILE FOR SQL LOADER | 11:00 A.M TO 12:30 P.M | CTL FILE TO LOAD DATA TO STAGING TABLE:= REQUISITION_04_CTL | 2019-05-31 | 2019-05-31 | COMPLETED | SQL*Loader-350: Syntax error, SQL*Loader-500: Unable to open file
3 |  | CREATING CONCURRENT EXECUTABLE AND PROGRAM | 2:00 P.M TO 3:30 P.M | EXCECUTABLE TO RUN THE CTL FILE:= REQUISITION_STG_GRP_04 PROGRAM TO RUN THE CTL FILE:= REQUISITON_STG_GRP_04_PRG | 2019-05-31 | 2019-05-31 | COMPLETED
4 |  | LOADING DATA INTO STAGING TABLE | 3:30 P.M TO 5:30 P.M | XX_PO_REQ_TEMP_04 | 2019-05-31 | 2019-05-31 | COMPLETED | ORA-01722: invalid number
DAY 2
S.NO | DATE | ACTIVITY | TIME | DESCRIPTION | STARTING DATE | COMPLETION DATE | STATUS | ERRORS AND WARNINGS
1 | 2019-06-02 | CREATION OF DUMMY INTERFACE TABLES | 9:30 A.M TO 10:00 A.M | DUMMY INTERFACE TABLES:= PO_REQUISITIONS_INTF_04_2 EXE NAME:- REQUISITION_INTF_9770 | 2019-06-02 | 2019-06-02 | COMPLETED
2 |  | VALIDATIONS FOR THE DATA IN STAGING TABLE | 10:00 A.M TO 12:00 P.M | PROCEDURE FOR VALIDATING DATA AND INSERTING IT INTO INTERFACE TABLES:= PO_REQUISITION_IFACE_04 | 2019-06-02 | 2019-06-02 | COMPLETED | 1:ORA-01722: invalid number ORA-06512: at "APPS.SP_PO_INTERFACE_DUMMY_04", line 23 ORA-06512: at line 1
3 |  | MOVING DATA TO THE TEMPORARY INTERFACE TABLE AND CHECKING THE VALIDATIONS | 12:30 P.M T0 2:00 P.M | EXECUTABLE NAME:= REQUISITION_GRP04_EXE PROGRAM NAME:= REQUISITION_GRP04_PRG | 2019-06-02 | 2019-06-02 | COMPLETED | NO ERROR
4 |  | CHECKING IMPORT PROGRAM | 2:00 P.M TO 2:30 P.M | REQUISITION OPEN INTERFACE IMPORT | 2019-06-02 | 2019-06-02 | COMPLETED
5 |  | MOVING DATA TO ACTUAL INTERFACE TABLES | 2:30 P.M TO 3:00 P.M | ACTUAL INTERFACE TABLES ARE:= PO_REQUISITIONS_INTERFACE_ALL | 2019-06-02 | 2019-06-02 | COMPLETED | NO ERROR
6 |  | MOVING DATA FROM INTERFACE TABLE TO BASE TABLE | 3:30 P.M TO 4:30 P.M | BASE TABLES : PO_REQUISITION_HEADERS_ALL PO_REQ_DISTRIBUTIONS_ALL PO_REQUISITION_LINES_ALL UPDATED BY FEB19_LC1_04 DATA | 2019-06-02 | 2019-06-02 | COMPLETED
7 |  | PROJECT 2 SILICON PRODUCT REQUESTIONS PART DISCUSSION | 4:30 P.M TO 5:30 P.M |  | 2019-06-02 | 2019-06-02
DAY 3
S.NO | DATE | ACTIVITY | TIME | DESCRIPTION | STARTING DATE | COMPLETION DATE | STATUS | ERROR AND WARNINGS
1 | 2019-06-03 | CREATING REPORT | 9:30 A.M TO 11:00 A.M | REPORT NAME:= REQUISITION_REPORT_9770 | 2019-06-03 | 2019-06-03 | COMPLETED | NO ERROR
2 |  | CREATING REPORT EXECUTABLE AND REPORT PROGRAM | 11:00 A.M TO 12:00P.M | EXECUTABLE TO RUN REPORT:= REQUISITION_GRP04_EXE PROGRAM TO RUN REPORTNAME:= REQUISITION_GRP04_PRG VALUESET:=CURR_CODE_VS | 2019-06-03 | 2019-06-03 | COMPLETED | NO ERROR
3 |  | CREATING REPORT FEATURES IN XML PUBLISHER | 12:00P.M TO 12:30 P.M | REQUISITION_GRP_04_PRG_040619 | 2019-06-03 | 2019-06-03 | COMPLETED | NO ERROR
4 |  | CREATING DATA DEFINATION CODE AND DATA TEMPLATE | 2:00 P.M TO 2:30 P.M | DATA DEFINITION:= REQUISITION_GRP04_DD DATA TEMPLATE:= REQUISITION_GRP04_DT | 2019-06-03 | 2019-06-03 | COMPLETED | NO ERROR
5 |  | CHECKING REPORT PROGRAM WITH DATA TEMPLATE | 2:30 P.M TO 3:30 P.M | DT CODE:=REQUISITION_GRP04_DTC | 2019-06-03 | 2019-06-03 | COMPLETED | NO ERROR
6 |  | WORKFLOW | 3:30 P.M TO 4:00 P.M | REQUISITION_GROUP_04 | 2019-06-03 | 2019-06-03 | COMPLETED
7 |  | DOCUMNETATION | 4:00 P.M TO 5:30 P.M |  | 2019-06-03 | 2019-06-03 | IN PROCESS

## SUPPLIER
EMPLOYEE NAME : VIJAY PAL EMPLOYEE_ID:1039767 GROUP NO:04 |  | DAILY EFFORT TRACKER
DAY 1
S.NO | DATE | ACIVITY | TIME | DESCRIPTION | STARTING DATE | COMPLETION DATE | STATUS | ERRORS AND WARNINGS
1 | 2019-05-31 | IDENTIFICATION OF DATA IN CSV | 9:30 A.M TO 10:30 A.M | LEGACY FILE:= SUPPLIER_LEGACY
2 |  | CREATING CTL FILE FOR SQL LOADER | 11:00 A.M TO 12:30 P.M | CTL FILE TO LOAD DATA TO STAGING TABLE:= XX_SUPPLIER_TEMP_04_CTL | 2019-05-31 | 2019-05-31 | COMPLETED | SQL*Loader-350: Syntax error Rectification
3 |  | CREATING CONCURRENT EXECUTABLE AND PROGRAM | 2:00 P.M TO 3:30 P.M | EXCECUTABLE TO RUN THE CTL FILE:= XX_SUPPLIER_TEMP_04_CTL_EXE PROGRAM TO RUN THE CTL FILE:= XX_SUPPLIER_TEMP_04_CTL_PRG | 2019-05-31 | 2019-05-31 | COMPLETED
4 |  | LOADING DATA INTO STAGING TABLE | 3:30 P.M TO 5:30 P.M | XX_SUPPLIER_TEMP_04 | 2019-05-31 | 2019-05-31 | COMPLETED | ORA-01722: invalid number RECTIFICATION
DAY 2
S.NO | DATE | ACTIVITY | TIME | DESCRIPTION | STARTING DATE | COMPLETION DATE | STATUS | ERRORS AND WARNINGS
1 | 2019-06-02 | CREATION OF DUMMY INTERFACE TABLES | 9:30 A.M TO 10:00 A.M | DUMMY INTERFACE TABLES:= AP_SUPPLIERS_INT_DUMMY_G04, SP_AP_SUP_SITES_DM_INT_04 | 2019-06-02 | 2019-06-02 | COMPLETED
2 |  | VALIDATIONS FOR THE DATA IN STAGING TABLE | 10:00 A.M TO 12:00 P.M | PROCEDURE FOR VALIDATING DATA AND INSERTING IT INTO INTERFACE TABLES:= SP_SUPPLIERS_INT_DUMMY_04, SP_AP_SUP_SITES_DM_INT_04 SEQUENCES:= VENDOR_INTERFACE_ID: SEQ_VENDOR_INT_ID_G04 VENDOR_SITE_INTERFACE_ID: SEQ_VENDOR_SITE_INT_ID_G04 | 2019-06-02 | 2019-06-02 | COMPLETED | NO REEOR
3 |  | MOVING DATA TO THE TEMPORARY INTERFACE TABLE AND CHECKING THE VALIDATIONS | 12:30 P.M T0 2:00 P.M | EXECUTABLE NAME:= SP_SUPPLIERS_DUMMY_INT_04_EXE, SP_AP_SUP_SITES_DM_INT_04_EXE PROGRAM NAME:= SP_SUPPLIERS_DUMMY_INT_04_PRG, SP_AP_SUP_SITES_DM_INT_04_PRG | 2019-06-02 | 2019-06-02 | COMPLETED | NO ERROR
4 |  | CHECKING IMPORT PROGRAM | 2:00 P.M TO 2:30 P.M | SUPPLIER OPEN INTERFACE IMPORT, SUPPLIER SITES OPEN INTERFACE IMPORT | 2019-06-02 | 2019-06-02 | COMPLETED
5 |  | MOVING DATA TO ACTUAL INTERFACE TABLES | 2:30 P.M TO 3:00 P.M | PROCEDURE USED: SP_SUPPLIERS_INT_04, SP_AP_SUP_SITES_INT_04, ACTUAL INTERFACE TABLES ARE:= SP_SUPPLIERS_INT, SP_SUPPLIER_SITES_INT EXECUTABLE NAME:= SP_SUPPLIERS_INT_04_EXE, SP_AP_SUP_SITES_INT_04_EXE PROGRAM NAME:= SP_SUPPLIERS_INT_04_PRG, SP_AP_SUP_SITES_INT_04_PRG | 2019-06-02 | 2019-06-02 | COMPLETED | NO ERROR
6 |  | MOVING DATA FROM INTERFACE TABLE TO BASE TABLE | 3:30 P.M TO 4:30 P.M | BASE TABLES : PO_VENDORS,PO_VENDOR_SITES_ALL, AP_SUPPLIERS UPDATED WITH FEB19_LC1_04 DATA | 2019-06-02 | 2019-06-02 | COMPLETED
7 |  | PROJECT 2 SILICON PRODUCT SUPPLIERS PART DISCUSSION | 4:30 P.M TO 5:30 P.M |  | 2019-06-02 | 2019-06-02
DAY 3
S.NO | DATE | ACTIVITY | TIME | DESCRIPTION | STARTING DATE | COMPLETION DATE | STATUS | ERROR AND WARNINGS
1 | 2019-06-03 | CREATING REPORT | 9:30 A.M TO 11:00 A.M | REPORT NAME:= COUNTRY_WISE_LIST_OF_SUP_G04 | 2019-06-03 | 2019-06-03 | COMPLETED | NO ERROR
2 |  | CREATING REPORT EXECUTABLE AND REPORT PROGRAM | 11:00 A.M TO 12:00P.M | EXECUTABLE TO RUN REPORT:= COUNTRY_WISE_LIST_OF_SUP_G04_E PROGRAM TO RUN REPORTNAME:= COUNTRY_WISE_LIST_OF_SUP_G04_P VALUESET:=P_COUNTRY_TVS_04, P_SHIP_TO_LOC_ID_TVS_04 | 2019-06-03 | 2019-06-03 | COMPLETED | NO ERROR
3 |  | CREATING REPORT FEATURES IN XML PUBLISHER | 12:00P.M TO 12:30 P.M | COUNTRY_WISE_XML_LIST_OF_SUP_G04_P_04 | 2019-06-03 | 2019-06-03 | COMPLETED | NO ERROR
4 |  | CREATING DATA DEFINATION CODE AND DATA TEMPLATE | 2:00 P.M TO 2:30 P.M | DATA DEFINITION:= COUNTRY WISE LIST OF SUPPLIER DD 04 DATA TEMPLATE:=COUNTRY WISE LIST OF SUPPLIER DT 04 | 2019-06-03 | 2019-06-03 | COMPLETED | NO ERROR
5 |  | CHECKING REPORT PROGRAM WITH DATA TEMPLATE | 2:30 P.M TO 3:30 P.M | DT CODE:= COUNTRY_WISE_LIST_OF_SUPPLIER_DT_04 | 2019-06-03 | 2019-06-03 | COMPLETED | NO ERROR
6 |  | WORKFLOW | 3:30 P.M TO 4:00 P.M | ITEM TYPE : RCN_G04, PROCESS : RCN_G04_PROCESS, ITEMKEY : SEQ_RCN_ITEMKEY_G04, PROCEDURE : SUP_DTL_REPORT_NOTIF_GEN_G04 | 2019-06-03 | 2019-06-03 | COMPLETED | NO ERROR
7 |  | DOCUMNETATION | 4:00 P.M TO 5:30 P.M |  | 2019-06-03 | 2019-06-03 | IN PROCESS

## INVOICES
EMPLOYEE NAME : GOWRI SHANKER EMPLOYEE_ID:1039774 GROUP NO:04 |  | DAILY EFFORT TRACKER
DAY 1
S.NO | DATE | ACIVITY | TIME | DESCRIPTION | STARTING DATE | COMPLETION DATE | STATUS | ERRORS AND WARNINGS
1 | 2019-05-31 | IDENTIFICATION OF DATA IN CSV | 9:30 A.M TO 10:30 A.M | LEGACY FILE:= INVOICE_LEGACY_FEB19_04
2 |  | CREATING CTL FILE FOR SQL LOADER | 11:00 A.M TO 12:30 P.M | CTL FILE TO LOAD DATA TO STAGING TABLE:= invoice_ctl_feb19_04 | 2019-05-31 | 2019-05-31 | COMPLETED | SQL*Loader-350: Syntax error Expecting "," or ")", found "to_date" INVOICE_DATE to_date('Mm/dd/yyyy')
3 |  | CREATING CONCURRENT EXECUTABLE AND PROGRAM | 2:00 P.M TO 3:30 P.M | EXCECUTABLE TO RUN THE CTL FILE:= invoice_migration_04_exe PROGRAM TO RUN THE CTL FILE:= invoice_migration_04_prg | 2019-05-31 | 2019-05-31 | COMPLETED
4 |  | LOADING DATA INTO STAGING TABLE | 3:30 P.M TO 5:30 P.M | XX_AP_INVOICES_FEB19_TEMP_04 | 2019-05-31 | 2019-05-31 | COMPLETED | ORA-01858: a non-numeric character was found where a numeric was expected
DAY 2
S.NO | DATE | ACTIVITY | TIME | DESCRIPTION | STARTING DATE | COMPLETION DATE | STATUS | ERRORS AND WARNINGS
1 | 2019-06-02 | CREATION OF DUMMY INTERFACE TABLES | 9:30 A.M TO 10:00 A.M | DUMMY INTERFACE TABLES:= ap_invoices_interface_dummy ap_invoices_dummy | 2019-06-02 | 2019-06-02 | COMPLETED
2 |  | VALIDATIONS FOR THE DATA IN STAGING TABLE | 10:00 A.M TO 12:00 P.M | PROCEDURE FOR VALIDATING DATA AND INSERTING IT INTO INTERFACE TABLES:= sp_invoice_conversion_04 SEQUENCE:=invoice_seq_1039774 | 2019-06-02 | 2019-06-02 | COMPLETED | NO ERROR
3 |  | MOVING DATA TO THE TEMPORARY INTERFACE TABLE AND CHECKING THE VALIDATIONS | 12:30 P.M T0 2:00 P.M | EXECUTABLE NAME:= INVOICE_CONVERSION_04_EXE PROGRAM NAME:= INVOICE_CONVERSION_04_PRG | 2019-06-02 | 2019-06-02 | COMPLETED | NO ERROR
4 |  | CHECKING IMPORT PROGRAM | 2:00 P.M TO 2:30 P.M | PO OPEN INTERFACE IMPORT | 2019-06-02 | 2019-06-02 | COMPLETED
5 |  | MOVING DATA TO ACTUAL INTERFACE TABLES | 2:30 P.M TO 3:00 P.M | ACTUAL INTERFACE TABLES ARE:= ap_invoice_lines_interface ap_invoices_interface | 2019-06-02 | 2019-06-02 | COMPLETED | NO ERROR
6 |  | MOVING DATA FROM INTERFACE TABLE TO BASE TABLE | 3:30 P.M TO 4:30 P.M | BASE TABLES : ap_invoices_all | 2019-06-02 | 2019-06-02 | COMPLETED
7 |  | PROJECT 2 SILICON PRODUCT INVOICES PART DISCUSSION | 4:30 P.M TO 5:30 P.M |  | 2019-06-02 | 2019-06-02
DAY 3
S.NO | DATE | ACTIVITY | TIME | DESCRIPTION | STARTING DATE | COMPLETION DATE | STATUS | ERROR AND WARNINGS
1 | 2019-06-03 | CREATING REPORT | 9:30 A.M TO 11:00 A.M | REPORT NAME:= invoice_report_feb19_04 | 2019-06-03 | 2019-06-03 | COMPLETED | NO ERROR
2 |  | CREATING REPORT EXECUTABLE AND REPORT PROGRAM | 11:00 A.M TO 12:00P.M | EXECUTABLE TO RUN REPORT:= invoice_report_feb19_04_exe PROGRAM TO RUN REPORTNAME:= invoice_report_feb19_04_prg VALUESET:=vs_invoice_curr_code | 2019-06-03 | 2019-06-03 | COMPLETED
3 |  | CREATING REPORT FEATURES IN XML PUBLISHER | 12:00P.M TO 12:30 P.M |  | 2019-06-03 | 2019-06-03 | COMPLETED
4 |  | CREATING DATA DEFINATION CODE AND DATA TEMPLATE | 2:00 P.M TO 2:30 P.M | DATA DEFINITION:= country wise dd 04 DATA TEMPLATE:= country wise dt 04 | 2019-06-03 | 2019-06-03 | COMPLETED
5 |  | CHECKING REPORT PROGRAM WITH DATA TEMPLATE | 2:30 P.M TO 3:30 P.M | DT CODE:=country_wise_dt_invoice_04 | 2019-06-03 | 2019-06-03 | COMPLETED
6 |  | WORKFLOW | 3:30 P.M TO 4:00 P.M | ITEM TYPE: PROCEDURE: SEQUENCE FOR ITEMKEY:= | 2019-06-03 | 2019-06-03 | COMPLETED
7 |  | DOCUMNETATION | 4:00 P.M TO 5:30 P.M |  | 2019-06-03 | 2019-06-03 | IN PROCESS