## DAY 1
DAILY EFFORT TRACKER
PLANNED ACTIVITIES | TRAINEE 1 ACTIVITIES(MODULE1) | TRAINEE 2 ACTIVITIES(MODULE 2) | TRAINEE 3 ACTIVITIES(MODULE3) | TRAINEE 4 ACTIVITIES(MODULE4) | ACTIVITY TIME | EMP_ID | TRAINEES | NAME
[6 empty] | 1039767 | TARINEE 1 | Vijay Pal
IDENTIFICATION OF DATA IN CSV | SUPPLIER_LEGACY | REQUISITION_LEGACY | PO_LEGACY | INVOICE_LEGACY_FEB19_04 | 9:30 A.M - 10:30 A.M | 1039770 | TRAINEE 2 | Aakash Shah
CREATING CTL FILE FOR SQL LOADER | XX_SUPPLIER_TEMP_04_CTL | REQUISITION_04_CTL | XX_PO_TEMP_04_CTL | XX_INVOICE_TEMP_04_CTL | 11:00 A.M - 12:30 P.M | 1039773 | TRAINEE 3 | Tannu Singh
CREATING EXECUTABLE | XX_SUPPLIER_TEMP_04_CTL_EXE | REQUISITION_STG_GRP_04 | XX_PURCHASE_ORD_04_EXE | INVOICE_MIGRATION_04_EXE | 14:15 P.M - 14:45 P.M | 1039774 | TRAINEE 4 | Gowri Shanker
CREATING CONCURRENT PROGRAM | XX_SUPPLIER_TEMP_04_CTL_PRG | REQUISITON_STG_GRP_04_PRG | XX_PURCHASE_ORD_04_PRG | INVOICE_MIGRATION_04_PRG | 14:45 P.M - 15:15 P.M
ERRORS RECTIFICATION | SQL*Loader-350: Syntax error Rectification | SQL*Loader-350: Syntax error, SQL*Loader-500: Unable to open file | Syntax error at line 39.Expecting "," or ")",found "VERIFY_FLAG". | SQL*Loader-350: Syntax error Expecting "," or ")", found "to_date" INVOICE_DATE to_date('Mm/dd/yyyy') | 15:15 P.M - 16:00 P.M
WARNINGS RECTIFICATION | ORA-01722: invalid number Rectification | ORA-01722: invalid number Rectification | ORA-01722: invalid number | ORA-01858: a non-numeric character was found where a numeric was expected | 16:30 P.M - 17:00 P.M
LOADING DATA INTO STAGING TABLE | XX_SUPPLIER_TEMP_04 | XX_PO_REQ_TEMP_04 | XX_PO_TEMP_04 | xx_ap_invoices_FEB19_temp_04 | 17:00 P.M - 17:30 P.M

## DAY 2
PLANNED ACTIVITIES | TRAINEE 1 ACTIVITIES(MODULE1) | TRAINEE 2 ACTIVITIES(MODULE 2) | TRAINEE 3 ACTIVITIES(MODULE3) | TRAINEE 4 ACTIVITIES(MODULE4) | ACTIVITY TIME
VALIDATIONS FOR THE DATA IN STAGING TABLE | DUMMY INTERFACE TABLE : AP_SUPPLIERS_INT_DUMMY_G04, SP_AP_SUP_SITES_DM_INT_04 INT EXE NAME: SP SUPPLIERS DUMMY INT 04 EXE,SP AP SUP SITES DM INT 04 EXE INT EXE SHORT NAME : SP_SUPPLIERS_DUMMY_INT_04_EXE, SP_AP_SUP_SITES_DM_INT_04_EXE INT PRG NAME : SP SUPPLIERS DUMMY INT 04 PRG,SP AP SUP SITES DM INT 04 PRG INT PRG SHORT NAME: SP_SUPPLIERS_DUMMY_INT_04_PRG, SP_AP_SUP_SITES_DM_INT_04_PRG SEQUENCES VENDOR_INTERFACE_ID: SEQ_VENDOR_INT_ID_G04 VENDOR_SITE_INTERFACE_ID: SEQ_VENDOR_SITE_INT_ID_G04 | PO_REQUISITIONS_INTF_04_2 ALL VALIDATIONS ARE DONE SUCCESSFULLY AS MENTIONED | DUMMY INTERFACE TABLE: PO_HEADERS_INTERFACE_DUMMY_04 DUMMY INTERFACE TABLE:PO_LINES_INTERFACE_DUMMY_04 DUMMY INTERFACE TABLE:PO_DIST_INTERFACE_D_04 SEQUENCES IHEADER_ID:SEQ_PO_HEADER_ID_04 LINE_ID:SEQ_PO_LINE_ID_04 DISTRIBUTION_ID:SEQ_PO_DISTRIBUTION_ID_04 | ALL VALIDATIONS ARE DONE | 9:30 A.M - 11:30 A.M
ERROR RECTIFICATION | NO ERRORS | NO ERROR | 1:ORA-01722: invalid number ORA-06512: at "APPS.SP_PO_INTERFACE_DUMMY_04", line 23 ORA-06512: at line 1 | ERROR | 11:30 A.M - 12:00 P.M
WARNING RECTIFICATION | NO WARNINGS | NO WARNINGS | NO WARNINGS |  | 12:00 P.M - 12:30 P.M
MOVING DATA TO THE TEMPORARY INTERFACE TABLE AND CHECKING THE VALIDATIONS | MAIN INT TABLE :SP_SUPPLIERS_INT, SP_SUPPLIER_SITES_INT EXE SHORT NAME : SP_SUPPLIERS_INT_04_EXE, SP_AP_SUP_SITES_INT_04_EXE EXE NAME:SP SUPPLIERS INT 04, SP AP SUP SITES INT 04 EXE PRG NAME:SP SUPPLIERS INT 04 PRG, SP AP SUP SITES INT 04 PRG PRG SHORT NAME:SP_SUPPLIERS_INT_04_PRG, SP_AP_SUP_SITES_INT_04_PRG | DUMMY INTERFACE TABLE:-PO_REQUISITIONS_INTF_04_2 EXE NAME:- REQUISITION_INTF_9770 | INTERFACE TABLES : Po_lines_interface, Po_headers_interface, Po_distributions_interface INTERFACE EXE NAME: XX_PO_INTERFACE_04_EXE INTERFACE PRG NAME : XX_PO_INTERFACE_04_PRG |  | 14:30 P.M - 15:30 P.M
CHECKING IMPORT PROGRAM | SUPPLIER OPEN INTERFACE IMPORT, SUPPLIER SITES OPEN INTERFACE IMPORT | REQUISITION OPEN INTERFACE IMPORT | PO OPEN INTERFACE IMPORT |  | 15:30 P.M - 16:00 P.M
MOVING DATA FROM INTERFACE TABLE TO BASE TABLE | PO_VENDORS,PO_VENDOR_SITES_ALL, AP_SUPPLIERS UPDATED WITH FEB19_LC1_04 DATA | PO_REQUISITION UPDATED | BASE TABLES : PO_HEADERS_ALL,PO_LINES_ALL, PO_DISTRIBUTIONS_ALL UPDATED BY FEB19_LC1_04 DATA |  | 16:30 P.M - 17:00 P.M
PROJECT 2 IDEA DISCUSSION | PROJECT 2 SILICON SUPPLIER PART DISCUSSION | PROJECT 2 SILICON REQUISITION PART DISCUSSION | PROJECT 2 SILICON PRODUCT PURCHASE ORDER PART DISCUSSION | PROJECT 2 SILICON PRODUCT INVOICES PART DISCUSSION | 17:00 P.M - 17:30 P.M

## DAY 3
PLANNED ACTIVITIES | TRAINEE 1 ACTIVITIES (MODULE1) | TRAINEE 2 ACTIVITIES (MODULE 2) | TRAINEE 3 ACTIVITIES (MODULE 3) | TRAINEE 4 ACTIVITIES (MODULE 4) | ACTIVITY TIME
CREATING REPORT | REPORT NAME : COUNTRY_WISE_LIST_OF_SUP_G04 | REQUISITION_REPORT_9770 | REPORT NAME:= ITEM_WISE_PO_DETAILS_04 |  | 9:30 A.M - 10:30 A.M
CREATING REPORT EXECUTABLE | EXE NAME:COUNTRY WISE LIST OF SUP G04 EXE, EXE SHORT NAME:COUNTRY_WISE_LIST_OF_SUP_G04_E | REQUISITION_GRP04_EXE | XX_PO_REP_04_EXE |  | 11:00 A.M. - 11:15 A.M.
CREATING REPORT PROGRAM | PRG NAME:COUNTRY WISE LIST OF SUP G04 PRG, PRG SHORT NAME:COUNTRY_WISE_LIST_OF_SUP_G04_P, VALUE SETS: P_COUNTRY_TVS_04, P_SHIP_TO_LOC_ID_TVS_04 | REQUISITION_GRP04_PRG | XX_PO_REP_04_PRG | IN PROCESS | 11:15 A.M - 11:30 A.M
CREATING REPORT FEATURES IN XML PUBLISHER | XML FILE :COUNTRY_WISE_XML_LIST_OF_SUP_G04_P_04, RTF FILE : COUNTRY_WISE_LIST_OF_SUP_G04_TEMPLET | CURR_CODE_VS | XX_PO_REP_04_PRG_040619 VALUESET:=VS_CURRENCY_CODE_04 |  | 11:30 A.M - 12:30 P.M
CREATING DATA DEFINATION CODE | DD NAME : COUNTRY WISE LIST OF SUPPLIER DD 04, DD CODE : COUNTRY_WISE_LIST_OF_SUP_G04_P | REQUISITION_GRP04_DD | XX_PO_REP_04_PRG_DD |  | 14:30 P.M - 15:00 P.M
CREATING DATA TEMPLATE | DT NAME : COUNTRY WISE LIST OF SUPPLIER DT 04 | REQUISITION_GRP04_DT | XX_PO_REP_04_PRG_DT |  | 15:00 P.M - 15:30 P.M
CHECKING REPORT PROGRAM WITH DATA TEMPLATE | DT CODE: COUNTRY_WISE_LIST_OF_SUPPLIER_DT_04 | REQUISITION_GRP04_DTC |  |  | 15:30 P.M - 16:00 P.M
WORKFLOW | ITEM TYPE : RCN_G04, PROCESS : RCN_G04_PROCESS, ITEMKEY : SEQ_RCN_ITEMKEY_G04, PROCEDURE : SUP_DTL_REPORT_NOTIF_GEN_G04 | REQUISITION_GROUP_04 | ITEM TYPE:PO049773 PROCEDURE:=SP_WORKFLOW_PO049773 SEQUENCE FOR ITEMKEY:=SEQ_ITEMKEY_773 |  | 16:30 P.M-17:30 P.M
ERROR RECTIFICATION | NO ERROR | NO ERROR | 1:ERRORS:=Routine FDPREP cannot read the file /ETAVIS/ETAVIS/fs1/EBSapps/appl/gl/12.0.0/reports/US/ITEM_WISE_PO_DETAILS_04.rep. RECTIFIED |  | 17:30 P.M - 18:00 P.M